## Multi Year
| 2021 Pre Estimate* |  | Actuals
| 2021 - Hi | 2021 - Lo | 2021 | 2020 | 2019 | 2018 | 2017 | 2016 | 2015 | 2014
Total Cost | 13781.25 | 11025 |  | 11288 | 13000 | 9000 | 7000 | 7085
Cost/Day | 2205 | 2205 |  | 2100 | 2000 | 1800 | 1400
Cost/Hr | 275.625 | 275.625 | 225 | 262.5 | 250 | 225 | 175
Hours | 50 | 40 |  | 43.0019 | 52 | 40 | 40
Days |  |  | 7 | 5 | 6.5 | 5 | 5
Slash Piles |  |  | 746 | 1050 | 1141 | 642 | 651 | 485 | 688 | 748
Sq Yards Max |  |  |  |  | 1350 | 1350 | 1350
*Estimate used the 2020 contract as basis

## 2021 Slash Piles
STREET SEGMENT INFORMATION | [7 empty] | SUMMARY INFORMATION
Seg | Street | 2020 Piles | 2021 30 May | 2021 Piles | Complete | Day | % Cmplt | Day Total | Piles | Hours / Cost Estimate |  |  | Loads | Notes
1 | Canopy | 4 | 6 | 6 | 6 | 2021-06-07 |  |  |  | Start Time | LD Hrs Estimate | Potential Hrs
2 | Forest Light 1 West | 10 | 8 | 8 | 8 | 2021-06-11 |  | 2021-06-07 | 87 | 830 | 6 | 8
3 | Forest Light 2 East | 55 | 36 | 52 | 52 | 2021-06-11 |  | 2021-06-08 | 84 | 830 | 6 | 8
4 | Hidden Rock 1 SW | 77 | 24 | 28 | 28 | 2021-06-07 |  | 2021-06-09 | 66 | 840 | 4 | 8 | 2 | Truck broke down 1 hour then equipment problems
5 | Hidden Rock 2 Middle | 82 | 41 | 69 | 69 | 2021-06-17 |  | 2021-06-10 | 105 | 840 | 6 | 8 | 3 | Left with tire rim problem
6 | Hidden Rock 3 NE | 9 | 20 | 22 | 22 | 2021-06-11 |  | 2021-06-11 | 149 | 1000 | 6 | 8 | 3? | 3 person crew. Flat tire in morning, notified.
7 | High Forest 1 West Entr | 1 | 0 | 0 | 0 | 2021-06-07 |  | Week 1 Total | 491
8 | High Forest 2 W of Waving | 26 | 22 | 21 | 21 | 2021-06-07 |  | 2021-06-17 | 91 |  | 6 | 8
9 | High Forest 3 E of Waving | 26 | 18 | 28 | 28 | 2021-06-07 | 5 on 6/8 | 2021-06-18 | 78 |  | 4 | 4 | 2? | Out by 1100, 3 man crew?
10 | High Forest 4 FL-HR | 16 | 9 | 13 | 13 | 2021-06-08 |  | 2021-06-23 | 86 |  | 5 | 5 |  | 3 man crew?
11 | High Forest 5 East | 54 | 28 | 66 | 66 | 2021-06-08 |  | Total | 746 |  | 43 | 57
12 | Mountain Dance 1 West | 12 | 41 | 71 | 71 | 2021-06-23 |  | Estimated Cost $ |  |  | 9675 | 12825
13 | Mountain Dance 2 Mid | 123 | 15 | 41 | 41 | 2021-06-10 | 20 on 6/11
14 | Mountain Dance 3 East | 36 | 4 | 11 | 11 | 2021-06-10
15 | Open Sky 1 N | 0 | 1 | 1 | 1 | 2021-06-10
16 | Open Sky 2 M | 53 | 39 | 87 | 87 | 6/9 - 15, | 6/10 72
17 | Open Sky 3 S | 64 | 37 | 44 | 44 | 2021-06-09
18 | Pine Air | 8 | 6 | 12 | 12 | 2021-06-18
19 | Secluded CR | 41 | 5 | 7 | 7 | 2021-06-09
20 | Serenity | 19 | 3 | 6 | 6 | 2021-06-23
21 | Timber Mdw 1 N Wldrot | 7 | 0 | 7 | 7 | 2021-06-11
22 | Timber Mdw 2 S Wldrot | 54 | 23 | 30 | 30 | 2021-06-11
23 | Waving Branch | 46 | 14 | 22 | 22 | 2021-06-17
24 | Wildroot | 42 | 1 | 10 | 10 | 2021-06-11
25 | Winding Trail 1 S Culd | 31 | 0 | 2 | 2 | 2021-06-07
26 | Winding Trail 2 S HFR | 9 | 11 | 7 | 7 | 2021-06-07
27 | Winding Trail 3 HFR - Serenity | 8 | 3 | 23 | 23 | 2021-06-18
28 | Winding Trail 4 North | 90 | 44 | 52 | 52 | 2021-06-23 | 9_6/18
| TOTAL | 1003 | 459 | 746 | 746 |  | 100%

## 2021 Chip Distribution
Status | Distance | Name |  | Location | Area/Cross Streets | Amount | Delivered | Contact P | Contact E
y | 3 | Laura Davis | 5.1 miles away, 9 minutes driving time, did site visit | 17815 Appaloosa Road | Canterbury Estates | As much as possible- 200 cu yd | 1 Full | 720-937-8153 | Laura via Nextdoor reply@rs.email.nextdoor.com | 2: 6/10
y | 7 | Lauri Gephart | 8.9 miles away, 12 minutes driving time; did site visit | 16170 Northcliff Square, Elbert |  | 1-3 Truckloads | 1 Full | goldenfan6@msn.com |  | 1: 6/10
y | HFR | Russ Huffman | next to or on top of the residual mulch that I had dumped last year. The dump location is to the east side of the circular driveway entrance. | 4422 Mountain Dance Drive |  | 1 loads / 10 cu yds | 1 Full | 719-930-8522
y | HFR | Ron Kelley |  | 15870 Winding Trail Rd |  | 1/2 truckload |  | 719 287-7807
y | HFR | Jen Tweden |  | 16212 Timber Meadow Dr |  | 1 load |  |  | cjtweden@gmail.com
y | HFR | Linda Klepacki Johnson | Drop in parking space near garage doors | 4841 High Forest Rd |  | 1 load |  | 928-242-2191 | linda.klepacki@gmail.com
y | Pickup | Tim S | Will pickup with his trailer | Homecrest circle | Eastwood Black Forest |  |  |  | Tim via Nextdoor reply@rs.email.nextdoor.com
y | Pickup | Shannon C | Will pickup with trailer |  | Briargate Homes |  |  |  | Shannon via Nextdoor reply@rs.email.nextdoor.com
y | Pickup | Madison Studholme |  | 1539 Yellow Tail Dr |  | 1 pickup truck load |  |  | Maddie Studholme <m.studholme3@gmail.com>

## 2021 Volunteer List
HFR 2021 Slash Mulch Volunteer List
Assignment | Monday | Tuesday | Wednesday | Thursday | Friday
Site Manager | Dave Schneider | Tom Nettles | Diane Kelsay | Dave Schneider | Gary Hoffman
Loader 1
Loader 2
Haul/Trailer 1 | Vic Russelavage (haul) | Vic Russelavage (haul) | Vic Russelavage (haul) | Vic Russelavage (haul) | Vic Russelavage (haul)
Haul/Trailer 2 | Dave Schneider (trailer) |  | Dave Schneider (trailer) | Dave Schneider (trailer) | Dave Schneider (trailer)
Helper 1 | Tom Nettles / help or site manage | Tom Nettles / help or site manage | Tom Nettles / help or site manage | Tom Nettles / help or site manage | Tom Nettles / help or site manage
Helper 2 |  |  |  | JD Dallager (am) | JD Dallager (am)
Helper 3 | Gary Hoffman PM | Gary Hoffman AM |  | Gary Hoffman AM
Helper 4
Helper 5
End of Day Check and Cleanup | Larry Dunn | Larry Dunn | Larry Dunn | Larry Dunn | Larry Dunn
Blue: Crew on Standby.
Contacts
Larry Dunn | 719.494.9009
Diane Kelsay | 719.494.7643
Gary Hoffman
Vic Russelavage <vicruss5@gmail.com>
Chris Schroeder | 719-330-3383 cell | limited avalability with family in town.
JD Dallager | 719-930-3874
J David Schneider | 505-670-1237
Tom Nettles
Contact
Front Range Arborists, Inc
5080 Geiger Blvd. Colorado Springs, CO. 80915
Office (719) 635-7459 Fax (719) 635-1206
www.frarborists.com
Charity Pacheco | Office Manager
Tom Flynn | President | tomflynn@frarborists.com

## 2021 Chip Distribution (2)
Status | Distance | Name |  | Location | Area/Cross Streets | Amount | Delivered | Contact P | Contact E
n | x | Es Kay Cozzi |  |  | N Woodmoor - Doewood & Aspenwood | 1 or 2 |  | (218)728-4200 | Es Kay via Nextdoor reply@rs.email.nextdoor.com
n | 2 | Jo Sammons/Dave Sammons | No longer needs | 17170 W Cherry Stage Rd 8 | Cherry Creek Crossing | 1 |  | 614-746-2407 | Jo/Dave via Nextdoor reply@rs.email.nextdoor.com
n | x | Angela Casarez |  | Hwy 105 near TLMFPD Sta 1 | Palmer Lake | several cubic yards |  | 719 696 9673 | aguarnere@gmail.com Angela via Nextdoor reply@rs.email.nextdoor.com
n |  | Laurie Polunci |  |  | The Timber? |  |  | 719-439-2485 | Laurie via Nextdoor reply@rs.email.nextdoor.com
n | 4 | Jessica Headley |  |  | Flying Horse |  |  |  | Jessica via Nextdoor reply@rs.email.nextdoor.com
y | Pickup | Tim S | Will pickup with his trailer | Homecrest circle | Eastwood Black Forest |  |  |  | Tim via Nextdoor reply@rs.email.nextdoor.com
y | 3 | Laura Davis | 5.1 miles away, 9 minutes driving time, did site visit | 17815 Appaloosa Road | Canterbury Estates | As much as possible- 200 cu yd | 1 Full | 720-937-8153 | Laura via Nextdoor reply@rs.email.nextdoor.com
n | x | Diane Betts |  | 845 Winding Hills Road. | Woodmoor & Top of the Moor - North Woodmoor |  |  | 719-488-1990 | Diane via Nextdoor reply@rs.email.nextdoor.com
n | 4 | Stacy Goff, |  | 14557 Westchester Dr | Gleneagle |  |  | 719.488.3850 | stacy.goff@gmail.com
n |  | Traci Merriman, |  |  | Trail Ridge North |  |  | 785-236-1874 | Traci via Nextdoor reply@rs.email.nextdoor.com
n | 4 | Barb Sullivan, |  |  | Milam and shoup- Black Forest Park |  |  |  | Barb via Nextdoor reply@rs.email.nextdoor.com
n | 4 | Tom Pasienski, |  | Kaibab Court | Abert Estates off Shoup |  |  |  | Tom via Nextdoor reply@rs.email.nextdoor.com
n | x | Maureen M (ask for Errol) |  |  | Latigo Trails |  |  | 719-3271303 | Maureen via Nextdoor reply@rs.email.nextdoor.com
n | x | Lori Castillo, |  | Woodmoor Acres Dr | Village Center at Woodmoor |  |  | 210-844-2191 | Lori via Nextdoor reply@rs.email.nextdoor.com
n |  | Joe Tourness, |  |  | Pine Creek | 1/2 ton truckload |  |  | Joe via Nextdoor reply@rs.email.nextdoor.com
y | Pickup | Shannon C | Will pickup with trailer |  | Briargate Homes |  |  |  | Shannon via Nextdoor reply@rs.email.nextdoor.com
n |  | Heather E |  |  | Divine Redeemer |  |  | 303-842-6349 (719)434-2840 | Heather via Nextdoor reply@rs.email.nextdoor.com
n |  | Kevin W |  |  | Highland Park |  |  | 719-321-7445 | Kevin via Nextdoor reply@rs.email.nextdoor.com
n | 4 | Kris & Brian Mack, |  | 12950 Thiebaud | Black Forest |  |  | 509-995-8860 | Kris via Nextdoor reply@rs.email.nextdoor.com
n |  | Regina P., |  |  | Wagon Trails |  |  | 719-660-9070 | Regina via Nextdoor reply@rs.email.nextdoor.com
y | 7 | Lauri Gephart | 8.9 miles away, 12 minutes driving time; did site visit | 16170 Northcliff Square, Elbert |  | 1-3 Truckloads | 1 Full | goldenfan6@msn.com
y | HFR | Russ Huffman | next to or on top of the residual mulch that I had dumped last year. The dump location is to the east side of the circular driveway entrance. | 4422 Mountain Dance Drive |  | 1 loads / 10 cu yds |  | 719-930-8522
y | HFR | Ron Kelley |  | 15870 Winding Trail Rd |  | 1/2 truckload |  | 719 287-7807
n | 4 | Stewart Cooper |  | Ridge Run | Black Forest & Hodgen |  |  | 719-310-9815
| x | Beyond 5 mile ring
y | HFR | Jen Tweden |  | 16212 Timber Meadow Dr |  | 1 load |  |  | cjtweden@gmail.com
y | Pickup | Madison Studholme |  | 1539 Yellow Tail Dr |  | 1 pickup truck load |  |  | Maddie Studholme <m.studholme3@gmail.com>
y | HFR | Linda Klepacki Johnson | Drop in parking space near garage doors | 4841 High Forest Rd |  | 1 load |  | 928-242-2191 | linda.klepacki@gmail.com